## Sheet1
USER STORY | TASKS | PRIORITY | DIFFICULTY | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11
AS AN EMPLOYEE I WANT TO LOGIN SO I CAN VIEW MY ACCOUNT. (9) | Design a Login screen. | Medium | 2 | DAY 1: Ready 0; DAY 2: Working 1; DAY 3: Complete 1
| Code to have two fields and a forgot password button. | High | 5 | DAY 1: Ready 2; DAY 2: Working 2; DAY 3: Working 2; DAY 4: Complete 1
| Code a verification process from login information. | High | 7 | DAY 2: Ready 2; DAY 3: Working 2; DAY 4: Working 2; DAY 5: Working 2; DAY 6: Complete 1
| Design and create a loading screen after login. | Low | 3 | DAY 4: Ready; DAY 5: Working 2; DAY 6: Complete 1
| Load the accounts calendar. | Low | 6 | DAY 11: Ready 1
AS A HR I WANT TO CREATE ACCOUNTS SO I CAN ADD EMPLOYEES. (9) | Have appropriate fields for HR to input users information. | High | 6 | DAY 7: Ready 0; DAY 8: Working 1; DAY 9: Working 1; DAY 10: Working 0; DAY 11: Working 0
| Store the persons inputs in their profile. | High | 5 | DAY 9: Ready 0; DAY 10: Working 1; DAY 11: Working 0
| Let HR assign the role and accesability for the account. | Low | 7 | DAY 9: Ready 0; DAY 10: Working 1; DAY 11: Working 2
| HR creates username and temporary password for the account. | High | 4 | DAY 9: Ready 0; DAY 10: Working 1; DAY 11: Working 2
| User can use the username and temp pass to login and change password. | Medium | 1 | DAY 11: Ready 0
Progress Points. |  |  | 51 Total | 49 left | 44 left | 41 left | 38 left | 34 left | 32 left | 32 left | 31 left | 30 left | 27 left | 7 left